## Manual Validation
CR / Bucket | CR Title | Manual Validation Task | Validation Type | Status | Owner | Evidence / Notes
A-1 | Product API channel availability filter | Scan dine-in QR → confirm dinein='No' items are absent from menu & search; ADD button hidden if any leak through. | Manual QA | Yet to test | Owner (real device) | PRODUCT_API_FIELD_MAPPING_A1_STATUS_2026-05-09.md §5.5
A-1 | Product API channel availability filter | Scan delivery URL (or switch via OrderModeSelector) → confirm delivery='No' items absent. | Manual QA | Yet to test | Owner (real device) | PRODUCT_API_FIELD_MAPPING_A1_STATUS_2026-05-09.md §5.5
A-1 | Product API channel availability filter | Scan takeaway URL → confirm takeaway='No' items absent. | Manual QA | Yet to test | Owner (real device) | PRODUCT_API_FIELD_MAPPING_A1_STATUS_2026-05-09.md §5.5
A-1 | Product API channel availability filter | Scan room QR → confirm same item set as dine-in (room shares dinein gate). | Manual QA | Yet to test | Owner (real device) | PRODUCT_API_FIELD_MAPPING_A1_STATUS_2026-05-09.md §5.5
A-1 | Product API channel availability filter | Cart full of dine-in-only items → toggle to delivery → confirm prompt appears with correct list; Cancel reverts; Confirm removes items. | Manual QA | Yet to test | Owner (real device) | PRODUCT_API_FIELD_MAPPING_A1_STATUS_2026-05-09.md §5.5
A-1 | Product API channel availability filter | Edit-order flow: previous items still render and are read-only (channel guard must NOT block previous-order display). | Regression | Yet to test | Owner (real device) | PRODUCT_API_FIELD_MAPPING_A1_STATUS_2026-05-09.md §5.5
R-1 | Room scanner WC context-preserve (G1) | Non-716 room scanner: place order #1, mark Paid in POS → place order #2 from same browser; expect order #2 still appears as Room X (NOT WC). | Manual QA | Yet to test | Owner (real scanner + POS) | ROOM_SCANNER_INTERMITTENT_WC_STATUS_2026-05-09.md
R-1 | Room scanner WC context-preserve (G1) | Same scenario with Cancellation (status 3) for order #1 instead of Paid. | Manual QA | Yet to test | Owner (real scanner + POS) | ROOM_SCANNER_INTERMITTENT_WC_STATUS_2026-05-09.md
R-1 | Room scanner WC context-preserve (G1) | Same scenario where status poll receives a transient 404 between orders (confirm via POS logs if observed). | Manual QA | Yet to test | Owner (real scanner + POS) | ROOM_SCANNER_INTERMITTENT_WC_STATUS_2026-05-09.md
R-1 | Room scanner WC context-preserve (G1) | Table scanner (non-room, non-716): confirm table dine-in still appears as Table X. | Regression | Yet to test | Owner (real scanner + POS) | ROOM_SCANNER_INTERMITTENT_WC_STATUS_2026-05-09.md
R-1 | Room scanner WC context-preserve (G1) | Walk-in scanner: confirm genuine walk-ins still appear as WC. | Regression | Yet to test | Owner (real scanner + POS) | ROOM_SCANNER_INTERMITTENT_WC_STATUS_2026-05-09.md
R-1 | Room scanner WC context-preserve (G1) | Restaurant 716 (Hyatt Centric): confirm behaviour identical to today — wipe still happens, customer is asked to re-pick room. | Regression | Yet to test | Owner (real scanner + POS) | ROOM_SCANNER_INTERMITTENT_WC_STATUS_2026-05-09.md
R-2 | Room availability / check-in gate Phase 1 | Scan room QR when room is vacant/available/checked-out → user cannot browse menu or place order. | Manual QA | Yet to test | Owner | ROOM_CHECKIN_GATE_AND_GUEST_AUTOPOPULATE_CR_PLAN_2026-02-XX.md
R-2 | Room availability / check-in gate Phase 1 | Scan room QR when room is occupied/checked-in → menu opens normally. | Manual QA | Yet to test | Owner | ROOM_CHECKIN_GATE_AND_GUEST_AUTOPOPULATE_CR_PLAN_2026-02-XX.md
R-3 | Room guest auto-populate + locked fields Phase 2 | Checked-in room: guest name and phone auto-populate from check-table-status and fields are locked (not editable). | Manual QA | Yet to test | Owner | ROOM_GUEST_AUTOPOPULATE_PHASE2_PLAN_2026-02-XX.md
R-3 | Room guest auto-populate + locked fields Phase 2 | Order payload carries autopopulated guest_name + guest_phone unchanged. | Manual QA | Yet to test | Owner | ROOM_GUEST_AUTOPOPULATE_PHASE2_PLAN_2026-02-XX.md
R-4 | Room pre-submit WC fallback guard | Confirm 716-only guard: room order cannot silently submit as table_id=0. Owner to decide whether to extend guard to all hotels. | Manual QA | Yet to test | Owner | ReviewOrder.jsx:983 (716 gate). Investigation needed for broader scope.
C-1 | Hide "Check In" system item from UI | Room order with Check In + normal items: OrderSuccess "Items Ordered (n)" hides Check In; count reflects only normal items. | Manual QA | Yet to test | Owner | CHECKIN_SYSTEM_ITEM_UI_LEAK_INVESTIGATION_2026-02-XX.md §10
C-1 | Hide "Check In" system item from UI | ReviewOrder "Previously Ordered" hides Check In; CartBar previousItemsCount excludes Check In. | Manual QA | Yet to test | Owner | CHECKIN_SYSTEM_ITEM_UI_LEAK_INVESTIGATION_2026-02-XX.md §10
C-1 | Hide "Check In" system item from UI | Bill Summary Item Total matches Subtotal and Grand Total (no off-by-one rupee). Tax/SC/GST unchanged. | Manual QA | Yet to test | Owner | CHECKIN_SYSTEM_ITEM_UI_LEAK_INVESTIGATION_2026-02-XX.md §10
C-1 | Hide "Check In" system item from UI | Order containing ONLY Check In: entire "Items Ordered" card is hidden (no "Items Ordered (0)"), no JS errors. | Manual QA | Yet to test | Owner | CHECKIN_SYSTEM_ITEM_UI_LEAK_INVESTIGATION_2026-02-XX.md §10
C-1 | Hide "Check In" system item from UI | Regression: order with no Check In renders all normal items exactly as before; totals match prior production. | Regression | Yet to test | Owner | CHECKIN_SYSTEM_ITEM_UI_LEAK_INVESTIGATION_2026-02-XX.md §10
D-1 | Delivery Address selected-address clarity | Default address auto-selects on load → DELIVERING TO header shows it; chosen card shows [Default] + green [SELECTED] pills + orange ✓ tick. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx (DELIVERING TO + da-card-selected-pill)
D-1 | Delivery Address selected-address clarity | Tap a non-default saved card → SELECTED pill + ✓ move to that card; [Default] pill stays on its original card; header text updates. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx
D-2 | Places autocomplete reverseAddress fix | Type a place name → pick a Places suggestion → Confirm & Proceed becomes clickable (reverseAddress populated). | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx (handleSelectPrediction sets setReverseAddress)
D-3 | GPS auto-detect when no default address | First-time user (no saved addresses, no default) → app prompts for location automatically; no misleading fallback selection. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx (needsGpsAutoDetect → applyCurrentLocation)
D-4 | Hide fallback marker when no active address | GPS denied & no saved address → map does NOT show red marker (no Shoghi/fallback marker leak). | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx:744 {hasActiveAddress && <Marker>}
D-5 | Disabled Confirm button visual state | No address selected → Confirm & Proceed button is grey (#ccc) with not-allowed cursor; turns orange when address is valid. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx:1028 backgroundColor: isContinueDisabled ? '#ccc' : primaryColor
D-6 | Not-deliverable helper text | Pick an out-of-range location → helper text appears: "Please choose another address closer to the restaurant." | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx:805 da-distance-no-hint
D-7 | In-form Use Current Location button | Open Add New Address form → "Use Current Location" visible inside form; tapping it auto-fills address/city/pincode. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx form-use-current-location-btn
D-8 | Empty-state Use Current Location button | No saved addresses → "Use Current Location" visible WITHOUT opening Add New Address form (now hosted in D-9 hero). | Manual QA | Yet to test | Owner (real device) | Consolidated into D-9 hero (empty-state-use-current-location-btn)
D-9 | Empty-state map replacement with centered CTA | No saved addresses + no active address: map is HIDDEN; centered hero shows "Where should we deliver?" + Use Current Location (primary) + Add New Address (secondary). | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx showEmptyHero / empty-state-hero. Bundle: main.018a3d4c.js
D-9 | Empty-state map replacement — GPS allowed | Tap Use Current Location on hero → GPS allowed → hero disappears, map appears with marker, distance check runs. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx (applyCurrentLocation success path)
D-9 | Empty-state map replacement — GPS denied | Tap Use Current Location → GPS denied → safe state, no marker, Confirm stays disabled. | Manual QA | Yet to test | Owner (real device) | DeliveryAddress.jsx (error path code=1)
D-9 | Empty-state geo-blocked inline help | Permission previously set to Block → inline help block visible on hero (Permissions API). Reset to Allow → help clears. | Manual QA | Yet to test | Owner (real device) | geoBlocked + Permissions API; testid empty-state-geo-blocked-help
D-9 | Saved address path unaffected | User with saved default address: map renders normally with marker; hero does NOT appear; saved cards visible. | Regression | Yet to test | Owner (real device) | showEmptyHero gate ensures hero only on empty + no-active state
P-1 | Phone country code not editable | iOS Safari + Android Chrome: country code is a picker (not editable text); user can change country via dropdown only. | Manual QA | Yet to test | Owner (real iPhone + Android) | react-phone-number-input in CustomerDetails.jsx + LandingCustomerCapture.jsx
P-2 | iPhone input zoom fix | Real iPhone Safari: tap any text input on delivery / customer-details / cooking-instructions forms → page does NOT auto-zoom. | Manual QA | Yet to test | Owner (real iPhone Safari) | 16px font-size enforced in CustomerDetails.css, ReviewOrder.css, CookingInstructionsModal.css